# Detailed guide on completing a supplier performance report

## Supplier performance reporting

The Ministerial Directions for Public Construction Procurement in Victoria require Victorian Government departments and state agencies (Agencies) to assess the performance of suppliers on a regular basis when undertaking public construction works or construction services when:

* for suppliers of Works - the value of the contract engaging the supplier is $750,000 (inclusive of GST) or higher; or
* for suppliers of Construction Services - the value of the contract engaging the supplier is $300,000 (inclusive of GST) or higher.

Further details on this requirement are available at [Supplier performance and shared reporting regime (Direction and Instruction 8.2)](https://www.dtf.vic.gov.au/ministerial-directions-and-instructions-public-construction-procurement/supplier-performance-and-shared-reporting-regime-direction-and-instruction-82).

[Defining public construction (Guidance 1.3b)](https://www.dtf.vic.gov.au/practitioners-toolkit-guidance-public-construction-procurement/defining-public-construction-public-construction-guidance-13b) sets out the definition of public construction and provides examples of what is considered works and construction related services.

## About this guide

This guide sets out the method to follow when assessing the performance of suppliers. This guide also establishes the grading scales to apply when assessing how suppliers perform.

This guide should be used by project and contract managers responsible to oversee contracts for works or construction services.

Using this guide will promote consistency, objectivity and transparency when assessing how suppliers perform.

## Contents of this guide

Supplier performance report template 2

How to use the grading scales for the attributes of performance 3

How to submit a performance report 3

What is public construction works and construction services 3

Grading scales for cost management 4

Grading scales for time management 5

Grading scales for standard of work 6

Grading scales for quality management 7

Grading scales for resource management 8

Grading scales for subcontractor management 9

Grading scales for contract administration 10

Grading scales for communications and relationships 11

Grading scales for occupational health and safety management 12

Grading scales for industrial relations 13

Grading scales for environmental management 14

Grading scales for Major Projects Skills Guarantee 15

Grading scales for Victorian Industry Participation Policy 15

## Supplier performance report template

In addition to any other means of assessing how suppliers perform, Agencies must use a common template to assess how suppliers perform.

The supplier performance report template includes questions on:

* Agency undertaking the assessment
* Details of Works or Construction Services that are being assessed
* Details of the supplier being assessed – company details and information on the supplier’s representative
* Period covered by the report
* Cost of the Works or Construction Services
* Time required for or taken to complete the Works or Construction Services
* Assessment of performance that considers thirteen attributes of performance
* Comment on the supplier’s performance
* Confirmation that the reporting officer has consulted with the supplier when preparing the report and that a copy pf the report was sent to the supplier
* Signature blocks for the reporting officer and validating officer

The following attributes of performance are assessed:

* Cost management
* Time management
* Standard of work
* Quality management
* Resource management
* Subcontractor management
* Contract administration
* Communications and relationships
* Occupational health and safety management
* Industrial relations management
* Environmental management
* Major Projects Skills Guarantee – performance under this policy
* Victorian Industry Participation Policy – performance under this policy

The assessment of performance is based on a five-level grading scale:

* Superior
* Good
* Acceptable
* Marginal
* Unsatisfactory

An option to mark an attribute as not applicable is available if the attribute is not relevant to the performance assessment.

## How to use the grading scale for the attributes of performance

### Assessing the attributes of performance

Consider whether the supplier’s performance during the reporting period met the graded criteria listed for each attribute.

Start with the lowest grading level for the attribute of performance being considered. If the supplier’s performance meets all the criteria listed for that grading level, consider whether the supplier meets the criteria for the next higher grading level. For example, when assessing the attribute of time management, if the supplier’s performance meets all criteria for an Acceptable rating, check to see if the supplier’s performance meets the criteria for a Good rating, and so on.

The supplier must be assessed for the next lower rating level if the supplier’s performance does not meet all the criteria for a grading level.

1. The following principles for evaluation should be used:
* Acceptable performance complies with contract requirements.
* For an Acceptable, Good or Superior rating, every one of the criteria for the rating level must be met.
* Marginal or Unsatisfactory ratings should be used if any one of the criteria has not been achieved.

Ratings should be supported by comments that set out the reasons for individual rating and overall performance assessment.

### Assessing the attributes of performance for Major Projects Skills Guarantee and Victorian Industry Participation Policy

If the policies for Major Projects Skills Guarantee or Victorian Industry Participation Policy do not apply to a contract, no assessment is required. Use the Not applicable grading by inserting a zero in the template.

## How to submit a performance report

Agencies submit performance reports at:

https://dtf.my.site.com/buyerportal/s/feedback-form

## Grading scales for cost management

Cost management is the process of planning and controlling the cost and allocated budget. Cost management is a form of management accounting that allows a business to predict impending expenditures to help reduce the chance of going over budget.

| **Unsatisfactory** | **Marginal** | **Acceptable** | **Good** | **Superior** |
| --- | --- | --- | --- | --- |
| **ANY ONE of the following occurred** | **ANY ONE of the following applied** | **ALL of the following applied** | **In addition to the requirements for an ‘Acceptable’ grading ALL of the following applied** | **In addition to the requirements for a ‘Good’ grading ALL of the following applied** |
| It is unlikely the required program of works can be delivered within the allocated contractual budgetSignificant variations and claims have been lodged that are unwarrantedProgress claim have been made with little or no activity on site to justify claims and the supplier has not provided a reasonable explanationThe supplier made no attempt to manage delays to mitigate cost and budget impacts Non-payment of sub-contractors claims for completed works are impacting on program of works schedule and performance | The supplier failed to meet one of the criteria required for an ‘Acceptable’ grading, but the failure did not attract an ‘Unsatisfactory’ grading | The program of works (including any claims submitted during the period) are within budget and met contract requirements (within the period specified)The supplier reviewed and reported progress regularly in line with contractual performance and payment milestonesUpdated programs of works including any claims and extension of works were submitted within the time specified or requestedProgress of program of work was managed in accordance with the program of works delivery schedule to enable and payment of claimsAll subcontractor claims for payment of completed works have been made | The program of works (including any updates submitted during the period) delivery performance has met all contract requirements, to permit progress paymentsThe supplier submitted program of works updates when any milestone completion date changed, without waiting for a request from the PrincipalUpdated program of work provided early warning of potential cost claims (if applicable)The supplier provided full and comprehensive information to support all lodged claims and requested variations.The supplier mitigated the cost impacts of delays by rescheduling and reallocating resources | The supplier strictly adhered to and exceeded the program of works performance scheduleThe supplier provided updated schedules whenever the sequencing of tasks changed to meet contract requirements (well before the period specified) without seeking variation in costsThe supplier made outstanding efforts to maintain progress and avoid delaysThe supplier mitigated the effects of anticipated delays by rescheduling and reallocating resources to delivery within the allocated budget |

## Grading scales for time management

Time management is the process of organising and implementing a strategy related to the time required for work activities on a project.

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Unsatisfactory** | **Marginal** | **Acceptable** | **Good** | **Superior** |
| **ANY ONE of the following occurred** | **ANY ONE of the following applied** | **ALL of the following applied** | **In addition to the requirements for an ‘Acceptable’ grading ALL of the following applied** | **In addition to the requirements for a ‘Good’ grading ALL of the following applied** |
| The required program of works has not been submittedThe program of works was not updated within the required number of days after a request from the PrincipalWork is not meeting scheduled progress AND it is unlikely that completion will be achieved by the approved completion date(s)There was little or no activity on site in the last two weeks and the Supplier has not provided a reasonable explanationThe supplier made no attempt to manage delays to mitigate their effects | The supplier failed to meet one of the criteria required for an ‘Acceptable’ grading, but the failure did not attract an ‘Unsatisfactory’ grading | The program of works (including any updates submitted during the period) met contract requirements (within the period specified)The supplier reviewed and reported progress regularly, rescheduled work activities to meet the program and updated the program of worksUpdated programs of works were submitted within the time specified or requestedAny updated program of works accurately reflected actual progressWork was managed in accordance with the program of works | The program of works (including any updates submitted during the period) met all contract requirements, including showing when action is required by the Principal to meet contract requirements (before the period specified)The supplier submitted program of works updates when any milestone completion date changed, without waiting for a request from the PrincipalUpdated program of work provided early warning of potential delays (if applicable)The program of works consistently demonstrated that approved completion date(s) would be metThe supplier allocated resources based on project needsThe supplier mitigated the effects of delays by rescheduling and reallocating resources | The supplier strictly adhered to the program of works, updating and resubmitting it whenever the sequencing of tasks changed to meet contract requirements (well before the period specified)The supplier made outstanding efforts to maintain progress and avoid delaysThe supplier mitigated the effects of anticipated delays by rescheduling and reallocating resources |

## Grading scales for standard of work construction

The standard of construction is ‘good workmanship’ This term, an industry standard, refers to the desired and acceptable standard of quality of work and materials on a construction project.

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Unsatisfactory** | **Marginal** | **Acceptable** | **Good** | **Superior** |
| **ANY ONE of the following occurred** | **ANY ONE of the following applied** | **ALL of the following applied** | **In addition to the requirements for an ‘Acceptable’ grading ALL of the following applied** | **In addition to the requirements for a ‘Good’ grading ALL of the following applied** |
| There was no evidence that the supplier has a system for identifying and rectifying defects; the Supplier relied on the Principal to identify defects At every site inspection the Principal identified defects that were not being addressedThe number of defects continued to increase as program of work progressed, with many outstanding for more than a monthThe supplier refused to acknowledge and rectify defects identified by the Principal | The supplier failed to meet one of the criteria required for an ‘Acceptable’ grading, but the failure did not attract an ‘Unsatisfactory’ grading | The supplier adhered to contract specifications The supplier consistently identified and rectified defects progressively as the program of work proceededWhenever inspected, the program of work had only a few minor defects and rectifying them did not affect the progress of the program of workThe supplier rectified defects identified by the Principal within the agreed timetable for rectification (unless prevented by circumstances beyond the Supplier’s control) | The supplier achieved better than specified tolerances and consistent high standards of workmanshipThe supplier provided detailed records of defect identification and rectificationThe supplier rectified defects identified by the Principal within required specified days (unless prevented by circumstances beyond the supplier’s control) | The supplier demonstrated that it considered defects to be unacceptableDuring inspections, the Principal did not identify any defects that were not already being actionedDefect-free completion was achieved (or appears likely to be achieved) by the approved completion date(s) |

## Grading scales for quality management

quality management is a collection of business processes focused on consistently meeting customer requirements and enhancing their satisfaction.

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Unsatisfactory** | **Marginal** | **Acceptable** | **Good** | **Superior** |
| ANY ONE of the following occurred | ANY ONE of the following applied | ALL of the following applied | In addition to the requirements for an ‘Acceptable’ grading ALL of the following applied | In addition to the requirements for a ‘Good’ grading ALL of the following applied |
| Program of work commenced on an activity before the required approval had been obtainedThe program of work was not ready for inspection at the notified time and as a result, the Principal had to re-visit the site Second or third party quality audit was carried out, the overall audit assessment was considered ‘Unsatisfactory’, OROverall audit assessment was ‘Marginal’ and the supplier did not address all non-conformancesThe supplier did not carry out its own inspections and audits but relied on the Principal to identify non-conformancesThe same non-conformance occurred two or more times | The Supplier failed to meet one of the criteria required for an ‘Acceptable’ grading, but the failure did not attract an ‘Unsatisfactory’ grading | The Supplier conducted the program of works in alignment to the Quality Management PlanProgram of work was ready for inspection at notified times for witness points and hold pointsIf a second or third party quality audit was carried out, the overall audit assessment was ‘Acceptable’ and the supplier addressed all non-conformancesThe supplier carried out its own site quality audits and regular inspections and provided evidence, within 14 days or the terms of the contract after the date of the audit, of both the immediate response and any system improvements proposed to close out all audit non-conformancesThe supplier’s quality system identified and dealt with most non-conformances without the Principal’s input | The supplier provided an internal audit schedule early in the contract period, updated it as necessary and adhered to the dates statedIf a second or third party quality audit was carried out, the overall audit assessment was **Good** and the supplier addressed all non-conformances within specified period | If a second or third party quality audit was carried out, the overall audit assessment was **Superior** and no non-conformances were identifiedThe supplier demonstrated a quality-oriented culture through routine involvement by senior managers in quality management on site, independent of any request from the Principal |

## Grading scales for resource management

Resource management the process of planning the resources including people necessary to meet the objectives of the project, and to satisfy the client's requirements. Construction resources might include: Products and materials, Construction plant and tools and equipment.

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Unsatisfactory** | **Marginal** | **Acceptable** | **Good** | **Superior** |
| **ANY ONE of the following occurred** | **ANY ONE of the following applied** | **ALL of the following applied** | **In addition to the requirements for an ‘Acceptable’ grading ALL of the following applied** | **In addition to the requirements for a ‘Good’ grading ALL of the following applied** |
| Key personnel were not appropriately skilledThere was no supervisor on site and the Principal had to deal directly with workers on more than 2 occasionsThere were insufficient resources to manage the program of workOn more than one occasion, the Principal found it difficult to contact appropriate personnel to discuss matters of concern Personnel were unfamiliar with the contract and rarely referred to itThe Supplier submitted Requests For Information when the information was in the contract; more than 3 times, the Principal’s responses simply identified relevant contract requirementsSite rules and procedures have not been establishedWorkers provided statutory evidence of not being paid | The supplier failed to meet one of the criteria required for an ‘Acceptable’ grading, but the failure did not attract an ‘Unsatisfactory’ grading | All personnel had appropriate skills for their tasks. The level of resources was adequate for the program of work activitiesThe supplier’s personnel ensured that workers followed contract requirements, with minimal intervention required from the PrincipalThe supplier established and maintained effective lines of communication with the Principal, minimising delays and re-workKey management personnel showed a good knowledge of contract requirements and followed specified procedures on most occasionsSite rules and procedures were established, together with measures to ensure they were followedThe supplier did not rely on the Principal’s expertise to inspect and verify specialist workThere was an appropriately skilled supervisor on site at all times | All the supplier’s personnel demonstrated knowledge and understanding of the parts of the contract relevant to their areas of responsibility requiring no intervention from the PrincipalSite rules and procedures were in place and were followed without exceptionThe supplier arranged for appropriate experts to inspect and verify specialist work, where the Supplier did not have the necessary expertise | All the supplier’s personnel demonstrated superior skills, more than adequate experience and a high level of professional courtesy when dealing with the Principal and the clientThe contract and the site were exceptionally well managed and the program of work proceeded efficiently, without any intervention from the Principal |

## Grading scales for subcontractor management

Subcontractor management is the practice of assigning part of the obligations and tasks under a contract to another party known as a subcontractor.

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Unsatisfactory** | **Marginal** | **Acceptable** | **Good** | **Superior** |
| **ANY ONE of the following occurred** | **ANY ONE of the following applied** | **ALL of the following applied** | **In addition to the requirements for an ‘Acceptable’ grading ALL of the following applied** | **In addition to the requirements for a ‘Good’ grading ALL of the following applied** |
| Subcontractors were not competent to undertake the program of work, causing re-work and delaysThere was no supervisor on site and the Principal had to deal directly with subcontractors on more than 2 occasionsThe supplier entered into subcontracts that did not include the specified provisions (for example, for payment, dispute resolution, insurance)The supplier relied on the Principal to review documents prepared by subcontractorsPoor subcontractor coordination/ supervision caused delays or significant re-work or poor quality completed workThe quality systems of subcontractors and the supplier were inconsistent, causing poor work qualitySubcontractor(s) were unaware of the quality, occupational health and safety, environmental, industrial relations, and where required the Major Projects Skills Guarantee objectives in the contractA subcontractor provided statutory evidence of not being paid entitlements | The supplier failed to meet one of the criteria required for an ‘Acceptable’ grading, but the failure did not attract an ‘Unsatisfactory’ grading | All subcontractors were suitably competent and experiencedAll subcontracts reviewed by the Principal included the required provisionsDesign and fabrication activities were well managed, with minimal non-conformances required to be resolved by the Principal except for faults in the Principal’s documentsThe quality systems of the subcontractors and the supplier were integrated to achieve satisfactory program of work qualitySubcontractor coordination issues caused only minor re-work, with no impact on contract time or the quality of the completed program of workThe supplier ensured all subcontractor claims were reviewed by people with relevant expertise and Security of Payment obligations were metThe supplier ensured that subcontractors complied with the occupational health and safety, environmental, industrial relations, and where required met the Major Projects Skills Guarantee objectives in the contract | All activities carried out by subcontractors were well managed, with no coordination problems apparent to the PrincipalThe quality, safety and environmental management systems of the Supplier and all subcontractors were seamlessly integratedSubcontractors demonstrated commitment to the quality, occupational health and safety, environmental, industrial relations, and where required the Major Projects Skills Guarantee objectives in the contract | All subcontracts reviewed included ‘back to back’ provisions with those in the contractSubcontractor relationships were exceptionally harmonious and the Principal observed an open collaborative relationship and communication between subcontractors and the supplier |

## Grading scales for contract administration / contract management

Contract administration is to obtain the supplies and services outlined in the contract, of the best quality, within a specific time frame and, most importantly, within budget. As such, contract administration serves as the primary part of the procurement process that assures that the contract is successfully executed.

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Unsatisfactory** | **Marginal** | **Acceptable** | **Good** | **Superior** |
| **ANY ONE of the following occurred** | **ANY ONE of the following applied** | **ALL of the following applied** | **In addition to the requirements for an ‘Acceptable’ grading ALL of the following applied** | **In addition to the requirements for a ‘Good’ grading ALL of the following applied** |
| The supplier did not notify a change to its authorised person for more than 2 days after the change occurredKey contact personnel were changed without notifying the PrincipalMore than 2 Requests For Information notifying ambiguities were submitted too late to avoid delaysMore than 2 claims for price or time adjustments were submitted more than a month after the related work was completedMore than 2 claims for adjustment did not include the required information, for example:* correct identification of the entitlement
* updated program
* evidence of costs

More than one payment claim did not include all the required information, including records of complianceMore than one progress report was received late or did not provide the required information | The supplier failed to meet one of the criteria required for an ‘Acceptable’ grading, but the failure did not attract an ‘Unsatisfactory’ grading | The supplier advised changes in contract personnel before they occurred (on the day they occurred if unforeseeable)The supplier provided proposals for variations by the specified time80% of Requests For Information notifying ambiguities were submitted within the specified timeThe supplier gave all notices (for example, for adverse Site Conditions) within the specified timesAll claims were submitted by the specified times, identified the entitlement (by reference to applicable contract provisions) and included relevant informationPayment claims were made in accordance with the contract, supported by the required informationThe supplier provided the required compliance documents on time, with only minor omissions that were readily correctedProgress reports included adequate information and were received on time | The supplier consistently provided proposals for variations before the specified timeAll Requests For Information notifying ambiguities were submitted within the specified timeClaims for adjustments were submitted within the specified time, correctly identified the source of the entitlement and included all the information required for assessmentPayment claims did not include claims for adjustments that had not been agreed | The supplier did not submit any documentation later than the specified timeThe Principal has not requested the supplier to provide any additional information for any claim, including payment claimsAll compliance documents were accurate and correct and none required amendment or resubmission |

## Grading scales for communications and relationships

Project communications and relations is about the interpersonal communication skills and ability to inspire and influence, communicate and build bonds. The ability to help and obtain change, develops, and resolves conflict.

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Unsatisfactory** | **Marginal** | **Acceptable** | **Good** | **Superior** |
| **ANY ONE of the following occurred** | **ANY ONE of the following applied** | **ALL of the following applied** | **In addition to the requirements for an ‘Acceptable’ grading ALL of the following applied** | **In addition to the requirements for a ‘Good’ grading ALL of the following applied** |
| The supplier demonstrated an adversarial approach and was unwilling to cooperate or communicate openly and or communicated only at meetings and through formal Requests For Information and claimsThe supplier cancelled or deferred more than 2 scheduled meetings without a reasonable explanation OR refused to attend for sufficient time to discuss critical mattersThe supplier refused to comply with a direction of the Principal, including: refusing to remove a person from the site when instructed, due to their inappropriate behaviour and or senior executive refused to meet to discuss formal issues OR was unavailable to meet within the specified time without good reasonMore than one payment claim was more than 20% above the value of work assessed by the Principal and or 50% or more of the Supplier’s claims were more than 25% above an independent estimate and or more than one claim, the Supplier refused to provide additional justificationOR refused to participate in negotiations and or the supplier initiated legal action before resolution processes were implemented | The supplier failed to meet one of the criteria required for an ‘Acceptable’ grading, but the failure did not attract an ‘Unsatisfactory’ grading | The supplier cooperated in all matters relating to the contract, for example accommodating the needs of the Principal, including those occupying the siteThe supplier acted within 1 day after any request to remove from the site a person who behaved inappropriatelyCommunication between supplier and Principal was open and effectiveThe supplier gave early warning of events significantly affecting the contract and worked with the Principal to achieve resolutionAll payment claims were discussed with the Principal and a reasonable value agreed for the completed work80% of claims for adjustment were approved within 10% of the initial claimThe supplier demonstrated commitment to informal dispute resolution processes, including a willingness of the senior executive to meet promptly to resolve issues | The supplier notified the Principal as soon as practicable, of all events that could affect the contract or the program of work and worked with the Principal to resolve the matter with minimal effects on contract time and priceAll payment claims were reasonable and were paid in fullAll claims for price and time adjustments were reasonable; 90% were paid in full, as initially claimed, AND agreement was reached on the quantum of the remainder by negotiation within the agreed timeframes after receiptThe supplier’s senior executive took a pro-active approach to preventing formal issues from arising, including attending meetings as necessary and maintaining a good relationship with the Principal’s senior executiveThe supplier showed commitment to informal dispute resolution processes; all issues and disputes were resolved the agreed timeframes | The supplier’s cooperation with the Principal and the Client has been outstanding and the client has not notified the Principal of a single complaintThe supplier managed the program of work, including all changes and delays, to minimise additional costs to the clientThe supplier’s senior executive showed exemplary leadership by:* attending start up workshop and close out workshop (if applicable)
* attending sufficient monitoring and contract administration meetings to maintain a good working relationship,
* regularly visiting the site
* maintaining frequent contact with the Principal’s senior executive, and
* initiating discussions to resolve emerging issues
 |

## Grading scales for occupational health and safety management

The object of occupational health and safety management is to secure the health, safety and welfare of employees and other persons at work, to eliminate, at the source, risks to health, safety or welfare of employees and other persons at work.

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Unsatisfactory** | **Marginal** | **Acceptable** | **Good** | **Superior** |
| **ANY ONE of the following occurred** | **ANY ONE of the following applied** | **ALL of the following applied** | **In addition to the requirements for an ‘Acceptable’ grading ALL of the following applied** | **In addition to the requirements for a ‘Good’ grading ALL of the following applied** |
| Site program of work started before the Occupational health and safety Management Plan was submittedThe supplier submitted an occupational health and safety Management Plan with major omissions and / or without site-specific risks or lateThe supplier failed to comply with occupational health and safety regulationsIf a second or third party audit was carried out the reports showed major non-conformance(s)The supplier did not carry out its own audits and site safety reviews but relied on the Principal to identify non-conformancesA notifiable occupational health and safety incident occurredA Prohibition Notice was imposed by WorkSafeOccupational health and safety reports were not provided | The supplier submitted an Occupational health and safety Management Plan with a few omissions that were readily rectified without causing delaysIf a second or third party audit was carried out the reports showed minor non-conformancesOccupational health and safety monthly reports were submitted late and /or included incomplete informationAn occupational health and safety incident was not reported to the Principal within 24 hrs after it occurredAn Improvement Notice was issued by a WorkSafe A Provisional Improvement Notice issued by issued by a health and safety representative is confirmed by a WorkSafe inspector | The Occupational health and safety Management Plan met all contract requirementsOccupational health and safety management complied with the contract, including relevant Victorian Government criteria for management systems and legislative requirementsThe site was kept clean and tidy and free of uncontrolled safety hazardsIf a second or third party audit was carried out the reports showed satisfactory performanceThere was no notifiable incidentOccupational health and safety reports were submitted on time and met contract requirements | There has been no lost time injury The supplier demonstrated commitment to the highest occupational health and safety standards and the safety of everyone on the siteThe supplier implemented a regular internal review processThe supplier’s project manager regularly conducts safety walks and was involved in safety events such as tool box talks, safety meetings | The supplier has demonstrated safety leadership through:* adopting a partnering approach with clients, subcontractors and WorkSafe
* the supplier’s executive involvement in safety management on site
* Second or third party audits were conducted and there were no non-conformances identified
* Comprehensive occupational health and safety management reporting demonstrating a safety culture (zero harm)
 |

## Grading scales for industrial relations management

Industrial relations management is the relationship between employers and employees in industry and the laws that affect it.

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Unsatisfactory** | **Marginal** | **Acceptable** | **Good** | **Superior** |
| **ANY ONE of the following occurred** | **ANY ONE of the following applied** | **ALL of the following applied** | **In addition to the requirements for an ‘Acceptable’ grading ALL of the following applied** | **In addition to the requirements for a ‘Good’ grading ALL of the following applied** |
| The supplier did not comply with the IR Plan (if applicable)The supplier breached the National Code of Practice (where applicable)Non-compliance with employment law obligations was identified (including a non-compliance by a subcontractor)An industrial relations incident, which could have been avoided if the supplier had taken reasonable, timely action, caused delays | A minor industrial relations incident occurred, which could have been avoided if the supplier had taken reasonable, timely action | The supplier complied with the industrial relations Plan (if required by the contract) and legal industrial relations obligationsThe supplier maintained a cooperative workplace environmentThe supplier identified and resolved any industrial relations issues within the supplier’s control | The supplier promptly identified and resolved any industrial relations issues, minimising delays to the program of workThe supplier demonstrated an understanding and took practical steps towards building a productive workplace culture with cooperative relations, effective communication and consultation | There have been no industrial relations issues The supplier has demonstrated leadership in industrial relations management through:* senior management involvement on site for industrial relations matters
* a productive workplace culture with cooperative relations, effective communication and consultation
* implementing a documented industrial relations management system demonstrating innovative functions and capability
* maintaining a strong internal review process
 |

## Grading scales for environmental Management

Environmental management is the management of environmental programs in a comprehensive, systematic, planned and documented manner. It includes the organisational structure, planning and resources for developing, implementing and maintaining policy for environmental protection.

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Unsatisfactory** | **Marginal** | **Acceptable** | **Good** | **Superior** |
| **ANY ONE of the following occurred** | **ANY ONE of the following applied** | **ALL of the following applied** | **In addition to the requirements for an ‘Acceptable’ grading ALL of the following applied** | **In addition to the requirements for a ‘Good’ grading ALL of the following applied** |
| The Environmental Management Plan was submitted lateThe supplier submitted an Environmental Management Plan with major omissions and / or without site-specific risksThe supplier failed to comply with environmental regulationsThe supplier did not carry out its own inspections and audits but relied on the Principal to identify non-conformancesSite reviews identified non-conformances with potential for regulatory intervention or Penalty Infringement NoticesIf a second or third party environmental audit was carried out and the audit report showed major non-conformance(s)A serious pollution incident occurredA Penalty Infringement Notice was imposed by regulatory authoritiesMonthly reports were not provided (if required) | The supplier submitted an Environmental Management Plan with a few omissions that were readily rectified without causing delaysIf a second or third party environmental audit was carried out the audit the report showed minor non-conformances | The Environmental Management Plan met the requirements of the contractThe supplier complied fully with the Environmental Management Plan and legislative requirementsThe site was kept clean and tidy, with appropriate environmental controls, regularly maintainedIf a second or third party environmental audit was carried out the audit the report showed satisfactory performanceThere was no notifiable environmental incident | There have been no environmental incidentsThe supplier demonstrated an understanding and took practical steps towards sustainabilityThe supplier implemented a regular internal review processThe supplier’s project manager regularly conducts environmental inspections and was involved in increasing environmental awareness through tool box talks and meetings | The supplier has demonstrated leadership in environmental management through:* a clear commitment to reaching new goals for environmental practices
* achieving new levels of sustainability
* senior management involvement in environmental matters on site
* implementing innovative environmental controls
* comprehensive environmental management reporting demonstrating an environmentally aware culture

Second or third party environmental audits were conducted and did not identify any non-conformances |

## Grading scales for Major Project Skills Guarantee

If required by the contract, the Major Projects Skills Guarantee requires all publicly funded works contracts with a pre-tender estimated value at or in excess of $20 million (inclusive of GST) to utilise Victorian registered apprentices, Victorian registered trainees or engineering cadets for at least 10% of the contract works’ total estimated labour hours. The Major Skills Guarantee Policy operates separately to the Victorian Industry Participation Policy.

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Unsatisfactory** | **Marginal** | **Acceptable** | **Good** | **Superior** |
| **ANY ONE of the following occurred** | **ANY ONE of the following applied** | **ALL of the following applied** | **In addition to the requirements for an ‘Acceptable’ grading ALL of the following applied** | **In addition to the requirements for a ‘Good’ grading ALL of the following applied** |
| The supplier did not comply with contractual obligations related to this policy | Not applicable | The supplier did not comply with contractual obligations related to this policy | Not applicable | Not applicable |

## Grading scales for Victorian Industry Participation Policy

The Victorian industry Participation Policy requires government departments and agencies to consider competitive local suppliers, including small and medium sized enterprises, when awarding contracts valued at:

* $1 million or more in regional Victoria, or
* $3 million or more in metropolitan Melbourne or for state-wide activities.

The Victorian industry Participation Policy gives particular attention to Strategic Projects, which are projects valued at $50 million or more or as otherwise agreed as strategic by government.

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Unsatisfactory** | **Marginal** | **Acceptable** | **Good** | **Superior** |
| **ANY ONE of the following occurred** | **ANY ONE of the following applied** | **ALL of the following applied** | **In addition to the requirements for an ‘Acceptable’ grading ALL of the following applied** | **In addition to the requirements for a ‘Good’ grading ALL of the following applied** |
| The supplier did not comply with contractual obligations related to this policy | Not applicable | The supplier complied with contractual obligations related to this policy | Not applicable | Not applicable |